## Ingrids log
Name: Ingrid Ionita |  | Project Group (Name/Number): Group 1
This activity log is for you to document your contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions. Or use this as a way to take notes for your own viewing
Week: | Date: | Activity/Task: | Time spent on Activity: | Completed? | Notes:
7 | 2022-08-16 | Spoke with the group outside of the session to discuss our ideas. Ideas to use for the project are gym membership database | 30 minutes | Yes | EXAMPLE
| 2022-10-19 | Created the slack channel for the group work. | 10 MNS | YES
| 2022-10-19 | Worked together after class to discuss what project we should choose. | 30 MNS | YES
| 2022-10-20 | Created the HW2 document that we submitted. | 1 HR | YES
| 2022-10-21 | Created the Trello board for the team to work on and to plan the project. | 15 MNS | YES
| 2022-10-22 | Discussed with the team on the task distribution and project approach, as well as a general timeline for the project deadline. Started at 5PM. | 1 HR | YES
| 2022-10-24 | Created the GoogleDrive folder for all of our work to store. | 10 MNS | YES
| 2022-10-25 | Further worked on the data analysis that Ayo has done. I just lowered the number of rows, because our data is too big! | 3 HRS | YES
| 2022-10-26 | Finalised the data cleaning process from my side. Made sure that the data is approved by the main analysts. | 2 HRS | YES
| 2022-10-27 | Re-cleaned the data, because I realised my mistake. I cleaned the datasets individually and then wanted to merge them, but then the numbers of rows didn't match up! | 5 HRS | YES
| 2022-10-27 | Worked on the HW2 document to better it. Our initial HW2 got a 75%, so we wanted to make it better and more specific. | 30 MNS | YES
| 2022-10-27 | Team meeting to discuss the project approach again; it was a little bit of an emergency meeting but we finally settled on what we are doing. I established myself as the scrum master and in charge of the group project activities. | 1 HR | YES
| 2022-10-28 | Worked on the project with Clarissa to analyse data. We worked on Q1 and got it halfway done. | 2 HR | YES
| 2022-10-29 | Worked on the project with Clarissa from 10:30AM until 3PM without any breaks. We finished Q1 and started working on Q2. | 5 HR 30 MNS | YES
| 2022-10-29 | The group joined together for a meeting to work on the data analysis. We began to look at Q3 as well and to fix some issues with our plots. | 1 HR | YES
| 2022-10-30 | Started to write the project documentation; mostly tried to make it look presentable and add headers. I wrote the Introduction and Background. | 2 HR | YES
| 2022-10-31 | Continued to shape the project report, specifically the parts that were not about the analysis. | 1 HR | YES
| 2022-11-01 | Finalised the step specifications and limitations. | 1 HR | YES
| 2022-11-01 | Worked with Michelle on the Q3 part, we couldn't figure out how to do Folium markers. | 1 HR | YES
| 2022-11-02 | Updated the tools and libraries section of the report. Worked on the API & geopy part of the code for Q3. | 4 HRS | YES
| 2022-11-02 | Team meeting to address the report analysis. Added Ayo's work on machine learning in the code and redistributed the questions to make sure they all get finalised. Clarissa - Q1, Ingrid - Q2, Michelle Q3. Ayo to support the writing of the project documentation and oversee the analysis (she finished her part on machine learning). | 40 MNS | YES
| 2022-11-05 | Worked on the project to put all parts together and pretty it up. | 2 HRS | YES
| 2022-11-06 | Meeting with Clarissa to go over the code and the project document | 30 MNS | YES
Total time:

## Clarissas log
Name: Hiu Ching (Clarissa) Lo |  | Project Group (Name/Number): Group 1
This activity log is for you to document your contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions. Or use this as a way to take notes for your own viewing
Week: | Date: | Activity/Task: | Time spent on Activity: | Completed? | Notes:
7 | 2022-08-16 | Spoke with the group outside of the session to discuss our ideas. Ideas to use for the project are gym membership database | 30 minutes | Yes | EXAMPLE
3 | 2022-10-20 | Researched on topic ideas and found potential datasets that we can use for our project (e.g., employee attrition rates dataset, bitcoin transaction dataset and student performance dataset). After thinking about it, I chose the employee attrition rates dataset and completed a homework 2 submission draft for the group (uploaded to the slack group). However, our group finally decided to proceed with another idea. | 1.5 hrs | Yes
3 | 2022-10-22 | Attended a meeting with our group to discuss about the work allocation, deadlines and housekeeping. I was allocated to work on the data analysis and visualisation. | 1 hr | Yes
4 | 2022-10-26 | Reviewed and amended the analysis plan. | 30 mins | Yes
4 | 2022-10-27 | Meeting with group to allocate the work. | 1 hr | Yes
4 | 2022-10-28 | Meeting with Ingrid to work on the analysis and visualisations. | 2 hrs | Yes
4 | 2022-10-29 | Meeting with Ingrid to work on Q1 and Q2 analyses and visualisations. | 5.5 hrs | Yes
4 | 2022-10-29 | Meeting with the whole group to continue our analysis. | 1 hr | Yes
5 | 2022-10-30 | Edited the project report document, mainly on the "tools and materials" part. | 1 hr
5 | 2022-10-31 | Worked on some more visualisations for Q1. Also worked on the project report document, added in the visualisations and analysis needed for the report. | 3 hrs | Yes
5 | 2022-11-01 | Organised files on github. | 30 mins | Yes
5 | 2022-11-02 | Meeting with the rest of the group to review the work we did. Also allocated the work regarding report write-up, Clarissa - Q1, Ingrid - Q2, Michelle - Q3. Ayo to support us with the write-up. | 1 hr | Yes
5 | 2022-11-03 | Worked on the report write up for Q1 and gave some comments regarding other parts of the report. | 3 hrs | Yes
5 | 2022-11-04 | Added the analysis and visualisation code to the github file. | 1 hr | Yes
5 | 2022-11-05 | Annotated and made changes to the code | 2 hrs | Yes
5 | 2022-11-05 | Formatted the report and made changes to Q1 writeup | 1 hr | Yes
5 | 2022-11-05 | Meeting with the group to run through the data analysis file. | 3 hrs | Yes
5 | 2022-11-06 | Made changes to the code mainly regarding the visualisation | 2 hrs | Yes
5 | 2022-11-06 | Met with Ingrid to review the code | 1 hr | Yes
Total time:

## Michelles log
Name: |  | Project Group (Name/Number): Group 1
This activity log is for you to document your contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions. Or use this as a way to take notes for your own viewing
Week: | Date: | Activity/Task: | Time spent on Activity: | Completed? | Notes:
7 | 2022-08-16 | Spoke with the group outside of the session to discuss our ideas. Ideas to use for the project are gym membership database | 30 minutes | Yes | EXAMPLE
| 2022-10-19 | had a group meeting where we discussed ideas on what topic to write on | 30 mins | YES
| 2022-10-22 | had a team meeting where task was distributed among all team members | 1HR | YES
| 6619226 | Had a group meeting where we became specific with the project approach | 1HR | YES
| 2022-10-29 | Joined in the team meet with other team members where we did some analysis on question 1 and question 2 | 3HRS | YES
| 2022-10-30 | Worked on question 3 to try figure out some plots and map for analysis | 3HRS | YES
| 2022-10-31 | Finalised on the maps and plots to use for analysis on question 3 | 4HRS | YES
| 2022-10-31 | discovered codes to help change longitude and latitude columns to specific location. wasn't working so i shared with ingrid to see if it wiill run from her side | 2HRS | YES
| 2022-10-31 | did a folium map for the project using relevant data but could not complete adding points to it | 1HR | YES
| 2022-11-01 | worked with ingrid on teh folium map and tried to figure out how to add pointers and also convert that loh and lat columns to specific locations | 1HRS | YES
| 2022-11-04 | completed teh report writing for question 3 | 3HRS | YES
| 2022-11-05 | Joined in a team meeting with teh team where we looked into teh codes. did some annotations and made sense of teh codes and how they relate with our question. created an outline for teh presentation slides and droped a to do list for everybody for finishing toches befoer we submit teh project. | 3HRS | YES
Total time:

## Ayos log
Name: |  | Project Group (Name/Number): Group 1
This activity log is for you to document your contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions. Or use this as a way to take notes for your own viewing
Week: | Date: | Activity/Task: | Time spent on Activity: | Completed? | Notes:
7 | 2022-08-16 | Spoke with the group outside of the session to discuss our ideas. Ideas to use for the project are gym membership database | 30 minutes | Yes | EXAMPLE
| 2022-10-19 | had a group meeting where we discussed ideas on what topic to write on | 30 mins | YES
| 2022-10-19 | had a team meeting where task was distributed among all team members | 1HR | YES
| 2022-10-20 | Shared ideas with the team on slack on suggested topic as well as submitted a word document showing likely questions that can be analysed in the project | 1HR | YES
| 2022-10-20 | Had team meeting and it was agreed I commence data cleaning on the adopted dataset | 1HR | YES
| 2022-10-21 | Data cleaning on-going | 3HRS | YES
| 2022-10-22 | Discussed with the team on the task distribution and project approach, as well as a general timeline for the project deadline. Started at 5PM. | 1HR | YES
| 2022-10-23 | Data cleaning on-going | 3HRS | YES
| 2022-10-24 | Data cleaning completed | 4HRS | YES
| 2022-10-27 | Goup meeting to further discuss the project | 1HR | YES
| 2022-10-28 | Machine learning modelling on-going | 6HRS | YES
| 2022-10-29 | The group joined together for a meeting to work on the data analysis. We began to look at Q3 as well and to fix some issues with our plots. | 1 HR | YES
| 2022-10-31 | Worked with Michelle on getting visuals for accident location | 1HR | YES
| 2022-11-01 | Machine learning modelling completed | 8HRS | YES
| 2022-11-02 | Worked on write up explaning the data cleaning and machine learning steps as well as the conclusion of the analysis | 4HRS | YES
| 2022-11-05 | Annotated the machine learning codes | 2HRS | YES
| 2022-11-05 | Meeting with the group to run through the Notebook | 1HR | YES
Total time: